## to be migrated
Scheduled migration date | APPL_DESCR | APPL_NAME from EAS database) | EAS, XAS or BlueStem app | Area | Dependencies (Tech or User) | Work Effort (High, Med or Low) | Inhouse or Vended App | Priority | Responsibility (Ours or Cas) | Direct Bind (Y or N) | UIC/UIS Portal Impacted | Application Production link | Migrated to SiteMinder Y/N | Application Owner | OWNER/Responsible for testing | Dependencies for testing | When to test/migrate? | Number of EAS sessions since 6/1/13 | Change Control needed | Communication Plan Needed
2014-07-16 | ALAS Web Application | edu.uillinois.aits.ALASFrontEnd | EAS | Finance | [5 empty] | N | Y | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://webprod.admin.uillinois.edu:443/alas/table_view.jsp | N |  | AITS TAM Finance/UAFR | none identified | with the next Finance upgrade | not needed
Need to identify owner(s) | appCardDeactivate | appCardDeactivate | EAS | [6 empty] | N | [7 empty] | 860
Unscheduled | Attribute Maintenance | edu.uillinois.aits.attribmaint | EAS | Student | [5 empty] | N |  |  |  |  | AITS TAM Student | none identified | Anytime | not needed
After November 2014 | AVSL | AVSL | EAS | HR/Pay | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv6.admin.uillinois.edu/appslogin/servlet/appslogin?appName=AVSL |  |  | AITS/ERHR | Upgrades | After November 2014 | not needed
After November 2014 | Banner Forms | edu.uillinois.aits.BannerGuiLogin | EAS | All | Tech needs to be migrated with Banner Workflow, |  |  |  |  | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://webprod.admin.uillinois.edu/bl/servlet/BannerLogin?x=88&appName=edu.uillinois.aits.BannerGui&fontParm=default&y=15 |  |  | AITS | Upgrades | After November 2014 | not needed
After November 2014 | Banner Forms | edu.uillinois.aits.BannerGui | EAS | All | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://webprod.admin.uillinois.edu/bl/servlet/BannerLogin?x=88&appName=edu.uillinois.aits.BannerGui&fontParm=default&y=15 |  |  | AITS | Upgrades | After November 2014 | not needed
After November 2014 | Banner Self-Service Application | edu.uillinois.aits.SelfServiceLogin | EAS | All | [5 empty] | N | Y | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://webprod.admin.uillinois.edu/ssa/servlet/SelfServiceLogin?appName=edu.uillinois.aits.SelfServiceLogin&dad=BANPROD1 |  |  | AITS | Upgrades | After November 2014 | not needed
After November 2014 | Banner Workflow | edu.uillinois.aits.WorkFlow | EAS |  | Tech needs to be migrated with Banner Forms |  |  |  |  | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://webprod.admin.uillinois.edu/bl/servlet/BannerLogin?appName=edu.uillinois.aits.WorkFlow | N |  | AITS TAM ODA | Upgrades | After November 2014 | not needed
After November 2014 | Benefits Pending Application | duplicate of HR Self-Service Application - Pending | EAS | HR/Pay | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv3.admin.uillinois.edu:443/ssa_pending/index_pending.jsp |  |  | AITS/UPB | Upgrades/PPACA | After November 2014 | not needed
Unscheduled | BRM Campaign Rules web app | edu.uillinois.aits.brmCampaignRules | EAS | Student | [5 empty] | N |  | https://webprod.admin.uillinois.edu/bl/servlet/BannerLogin?appName=edu.uillinois.aits.BRM |  |  | AITS ESC Student | Upgrades | Anytime | not needed
After November 2014 | Campus Recreation Application |  | EAS | HR/Pay | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv3.admin.uillinois.edu:443/ssaDeductions/ba_park_emp_search.jsp |  |  | AITS | Upgrades | After November 2014 | not needed
Working on Summer 2014 date | CCFD Report | edu.uillinois.aits.ccfdreport | EAS | HR/Pay | [5 empty] | N |  |  |  |  | AITS | other CCFD apps | Summer 2014 | not needed
Working on Summer 2014 date | CCFD Web Application | edu.uillinois.aits.ccfdweb | EAS | HR/Pay | [5 empty] | N |  |  |  |  | AITS | other CCFD apps | Summer 2014 | not needed
Working on Summer 2014 date | ccfdFilter | (WIDEMEMO) | XAS | [6 empty] | N |  |  |  |  | AITS | other CCFD apps | Summer 2014 | not needed
Working on Summer 2014 date | CCFDWebApp | (WIDEMEMO) | XAS | [6 empty] | N |  |  |  |  | AITS | other CCFD apps | Summer 2014 | not needed
Working on Summer 2014 date | ccfdwebfilter | (WIDEMEMO) | XAS | [6 empty] | N |  |  |  |  | AITS | other CCFD apps | Summer 2014 | not needed
After November 2014 | Charities Application |  | EAS | HR/Pay | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv3.admin.uillinois.edu:443/ssaDeductions/ba_park_emp_search.jsp |  |  | AITS | Upgrades | After November 2014 | not needed
Unscheduled due to application upgrade | Clarity |  | EAS | [6 empty] | Y |  | https://clarity.apps.uillinois.edu/niku/nu#action:npt.overview | N |  | AITS PMO |  |  | not needed | ? | ?
2014-07-22 | Codebook | edu.uillinois.aits.codebook | EAS | Student | [5 empty] | N |  | https://webprod.admin.uillinois.edu/codebook/jsp/index.jsp |  |  | AITS TAM Student | none identified | 2014-07-22 | not needed | N | N
Need to identify owner(s) | Collaborate Enterprise Objects App | edu.uillinois.aits.msgObjects | EAS | [6 empty] | N | [7 empty] | 337
After November 2014 | Collections Application |  | EAS | HR/Pay | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv3.admin.uillinois.edu:443/ssaDeductions/ba_park_emp_search.jsp |  |  | AITS | Upgrades | After November 2014 | not needed
2014-07-16 | Cross-FOAPAL Web Application | edu.uillinois.aits.foapal.webapp | EAS | Finance | [5 empty] | N | Y | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://webprod.admin.uillinois.edu:443/xcfoap/jsp/FOAPALMenu.jsp | N |  | AITS TAM Finance/UAFR | none identified | with the next Finance upgrade | not needed
Working on August 2014 date | DARSweb Student - UIC | darswebstu_uic | EAS | Student | [5 empty] | N |  |  |  |  | ADSD Development (Dave Wells) | Need to check with Dave Wells |  | not needed
Working on August 2014 date | DARSweb Student - UIS | darswebstu_uis | EAS | Student | [5 empty] | N |  |  |  |  | ADSD Development (Dave Wells) | Need to check with Dave Wells |  | not needed
Working on August 2014 date | DARSweb Student - UIUC | darswebstu_uiuc | EAS | Student | [5 empty] | N |  |  |  |  | ADSD Development (Dave Wells) | Need to check with Dave Wells |  | not needed
Need to identify owner(s) | Direct Deposit Application | edu.uillinois.aits.DirectDepositHelper | EAS | Finance | [5 empty] | N | [7 empty] | 0
Need to identify owner(s) | Direct Deposit Application | edu.uillinois.aits.directdeposit | EAS | Finance | [5 empty] | N | [7 empty] | thousands
Wait until end of IAM project. This application may be retired | EAS Administration Application | edu.uillinois.aits.EasAdminApplication | EAS | Security | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/jsp/login.jsp?redirect=https://eas.admin.uillinois.edu:443/easadmin/jsp/admin_search_user.jsp |  |  | Chris Barton |  |  | 12096
Need to identify owner(s) | EAS Login | edu.uillinois.aits.EasLogin | EAS | [6 empty] | N | [7 empty] | thousands
Need to identify owner(s) | EAS Test Suite Application | org.any-openeai-enterprise.TestSuiteApplication-Eas | EAS | [6 empty] | N | [7 empty] | 0
2014-07-22 | edu.uillinois.aits.BRM | edu.uillinois.aits.BRM | EAS | Student | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://webprod.admin.uillinois.edu/bl/servlet/BannerLogin?appName=edu.uillinois.aits.BRM |  |  | AITS ESC Student |  | 2014-07-22 | not needed | N | N
Need to identify owner(s) (no user sessions since 6/1/13) | edu.uillinois.aits.icc.example1 | (WIDEMEMO) | XAS | [6 empty] | N | [7 empty] | 0
Need to identify owner(s) | edu.uillinois.aits.OCP.VendorManagement | (WIDEMEMO) | XAS | [6 empty] | N | [7 empty] | thousands
After November 2014 | edu.uillinois.aits.prmstablemaint | edu.uillinois.aits.prmstablemaint | EAS | HR/Pay | [5 empty] | N |  |  |  |  | AITS | Pension Reform/Upgrades | After November 2014 | not needed
Need to identify owner(s) | edu.uillinois.aits.PRZM-X | (WIDEMEMO) | XAS | [6 empty] | N | [7 empty] | thousands
Unscheduled (probably Fall 2014) | edu.uillinois.aits.temprojcode | edu.uillinois.aits.temprojcode | EAS | Finance | [5 empty] | N |  |  |  |  | AITS TAM Finance/UPAY | none identified | In Fall
Need to contact Tony Kerber | edu.uillinois.uihr.HrNet | (WIDEMEMO) | XAS | HRIS | [5 empty] | N | [6 empty] | Tony Kerber will need to be involved in deciding. | 38
No users have logged in since 6/1/13. May not be migrated to SiteMinder | Employee Contact Information | edu.uillinois.aits.employeeContactInfo | EAS | [6 empty] | N | [7 empty] | 0
After November 2014 | Employee Mass Changes | duplicate of HR and Finance Employee Mass Change Application | EAS | HR/Pay | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv3.admin.uillinois.edu:443/hrpayempmasschg/jsp/home.jsp |  |  | AITS | Fiscal Year End/Upgrades | After November 2014 | 246
Need to identify owner(s) (no user sessions since 6/1/13) | Enterprise Session | edu.uillinois.aits.EnterpriseAuthenticationServlet | EAS | [6 empty] | N | [7 empty] | 0
Need to identify owner(s) (no user sessions since 6/1/13) | Enterprise User lookup -- UA Wireless | edu.uillinois.aits.uaguest | EAS | [6 empty] | N | [7 empty] | 0
Need to contact Ethics Office | Ethics | edu.uillinois.aits.ethics | EAS | Ethics Office | [5 empty] | N |  |  |  |  | Ethics Office | Annual Training | Need to contact Ethics Office | thousands
Need to contact Ethics Office | Ethics Training Administration Application | edu.uillinois.pb.EthicsTrainingAdministrationApplication | EAS | Ethics Office | [5 empty] | N |  |  |  |  | Ethics Office | Annual Training | Need to contact Ethics Office | 136
Unknown (Fall 2014) | Expanded ACH Information for Vendors | edu.uillinois.aits.expandedAch | EAS | Finance | [5 empty] | N |  |  |  |  | AITS TAM Finance/UPAY | none identified | In Fall | 0
2014-07-16 | FABWeb |  | EAS | Finance | [5 empty] | N | Y | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://apps.obfs.uillinois.edu/fixedassets/dsp_MainMenu.cfm |  |  | AITS TAM Finance/UAFR | none identified | In Fall | not needed
Need to contact Mark Baysore | FAMIS Application | edu.uillinois.aits.FamisBL | EAS | OCP | [5 empty] | N |  |  |  |  | Mark Baysore/OCP | Need to contact Mark Baysore | Need to contact Mark Baysore | 0
Unknown (Fall 2014) | Finance Banner Crosswalks | edu.uillinois.aits.foapalfrontend | EAS | Finance | [5 empty] | N |  |  |  |  | AITS TAM Finance/UAFR | none identified | In Fall | 1
Anytime | Financial Aid Front-ends | edu.uillinois.aits.finaidFrontEnds | EAS | Student | [5 empty] | N |  |  |  |  | AITS TAM Student | none identified | Anytime | 66
Need to contact Brian Schoudel | Gartner | edu.uillinois.aits.GartnerHelper | EAS | COE | [5 empty] | N |  | http://research.apps.uillinois.edu/gartner/ |  |  | Brian Schoudel |  |  | 544
with the next Finance upgrade | Grant Loader Interface | edu.uillinois.aits.grantloader | EAS | Finance | [5 empty] | N |  |  |  |  | AITS TAM Finance/GCO | with the next Finance upgrade | with the next Finance upgrade | 886
Unknown | Hire Touch Application | edu.uillinois.aits.HireTouchHelper | EAS | HRIS | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv6.admin.uillinois.edu/appslogin/servlet/appslogin?appName=edu.uillinois.aits.HireTouchHelper | N |  | Tony Kerber will need to be involved in deciding. | Tony Kerber will need to be involved in deciding. | Tony Kerber will need to be involved in deciding. | thousands
After November 2014 | HR and Finance Employee Mass Change Application (duplicate of Employee Mass Changes) | edu.uillinois.aits.hrPayEmpMassChg | EAS | HR/Pay | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv3.admin.uillinois.edu:443/hrpayempmasschg/jsp/home.jsp |  |  | AITS | Fiscal Year End/Upgrades | After November 2014 | 246
2014-07-16 | HR Finance Modification Front-end | edu.uillinois.aits.hrfinmodsfrontend | EAS | Finance | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv3.admin.uillinois.edu:443/hrfinmodsfrontend/index.jsp | [5 empty] | 111
After November 2014 | HR Self Service Application - Deductions (duplicate of Benefits Pending Application) | edu.uillinois.aits.hr.ssaDeductions | EAS | HR/Pay | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv3.admin.uillinois.edu:443/ssaDeductions/ba_park_emp_search.jsp |  |  | AITS | Upgrades | After November 2014 | not needed
After November 2014 | HR Self-Service Application - Pending | edu.uillinois.aits.hr.ssaPending | EAS | HR/Pay | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv3.admin.uillinois.edu:443/ssa_pending/index_pending.jsp |  |  | AITS/UPB | Upgrades/PPACA | After November 2014 | not needed
Will go with PARIS (probably December 2014) | HRFE | edu.uillinois.aits.hrFrontEnd | EAS | HR/Pay | [5 empty] | N |  |  | N |  | AITS/HR | After Fall 2014 Upgrades and Before the PARIS Prior Pay Adjustment Implementation in February 2015 | This will go with PARIS. Preferrably December 2014 | not needed
Unknown (Fall 2014) | iBuy Application | edu.uillinois.aits.iBuyHelper | EAS | Finance | [5 empty] | N |  |  |  |  | OBFS BIS/AITS TAM Finance | none identified | In Fall | not needed
September 2014 (testing to begin 1st of August) | iCard application |  | EAS | iCard office | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://www.icard.uillinois.edu/Login/dspindex.cfm |  |  | Kimber Blum/Scott Eichman |  |  | not needed | ? | ?
Need to identify owner(s) | iGrad Finanical for OBFS | iGradFinance | EAS | Finance | [5 empty] | N | [7 empty] | 31
Unknown (Fall 2014) | InfoEd | edu.uillinois.aits.InfoEdHelper | EAS | Research Administration | [5 empty] | N |  |  |  |  | Research Administration | InfoEd Upgrade | Fall 2014? | not needed
After November 2014 | Involuntary Deductions Application |  | EAS | HR/Pay | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv3.admin.uillinois.edu:443/invfrontend/index.jsp |  |  | AITS/UPB | Upgrades | After November 2014 | not needed
After November 2014 | Involuntary Web Application | edu.uillinois.aits.invfrontend | EAS | HR/Pay | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv3.admin.uillinois.edu:443/invfrontend/index.jsp |  |  | AITS/UPB | Upgrades | After November 2014 | not needed
Anytime | ISIR Transmissions | edu.uillinois.aits.isirTransmission | EAS | Student | [5 empty] | N |  |  |  |  | AITS TAM Student | none identified | Anytime | not needed
Need to identify owner(s) (no user sessions since 6/1/13) | ITPC | ITPC_Site | EAS | [6 empty] | N | [7 empty] | 0
Need to identify owner(s) (no user sessions since 6/1/13) | Job-share | edu.uillinois.job-share | EAS | [6 empty] | N | [7 empty] | 0
Need to identify owner(s) (4 user sessions since 6/1/13) | Letters of Education Online | edu.uillinois.aits.LEO | EAS | [6 empty] | N | [7 empty] | 4
Need to identify owner(s) (no user sessions since 6/1/13) | Luminis | edu.uillinois.aits.LuminisHelper | EAS | [6 empty] | N | [7 empty] | 0
need to check with UIC OAR | Mediease at UIC |  | EAS | Student | [5 empty] | Y |  |  | N |  | UIC OAR | need to check with UIC OAR | need to check with UIC OAR
2014-07-22 | OAR Student Vault Audit | edu.uillinois.aits.oarlegato | EAS | Student | [5 empty] | N |  | https://appserv3.admin.uillinois.edu/legato/ |  |  | AITS ADSD TAM Student/BDMS Team | none identified | 2014-07-22 | not needed | N | N
with the next Finance upgrade | OBFS Web Applications | edu.uillinois.obfs.Apps | EAS | Finance | [5 empty] | N |  |  |  |  | OBFS BIS/AITS TAM Finance | none identified | with the next Finance upgrade | not needed
Need to identify owner(s) | Parameter Editor | edu.uillinois.aits.parameditor | EAS | [6 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://webprod.admin.uillinois.edu:443/ParamFrontEnd/index.jsp | [5 empty] | thousands
After November 2014 | Parking Application |  | EAS | HR/Pay | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv3.admin.uillinois.edu:443/ssaDeductions/ba_park_emp_search.jsp |  |  | AITS | Upgrades | After November 2014 | not needed
Will go with HRFE (probably December 2014) | Payroll Adjustment Request Interface System (PARIS) |  | EAS | HR/Pay | [10 empty] | AITS/UPB | After Fall 2014 Upgrades and Before the PARIS Prior Pay Adjustment Implementation in February 2015 | This will go with HRFE. Preferrably December 2014 | not needed
2014-07-16 | P-Card Web Application | edu.uillinois.aits.PcardLogin | EAS | Finance | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://webprod.admin.uillinois.edu/ssa/servlet/SelfServiceLogin?appName=edu.uillinois.aits.PcardLogin | N |  | AITS TAM Finance/UPAY | none identified | In Fall | not needed
Need to ask Mark Thompson ((no user sessions since 6/1/13) | Placement and Proficiency (PNP)/Advance Placement (AP) Front-end | edu.uillinois.aits.pnpap | EAS | Need to ask Mark Thompson | [5 empty] | N |  |  |  |  | ADSD Development (Mark Thompson) | Need to ask Mark Thompson | Need to ask Mark Thompson | 0
Need to contact Tony Kerber | Positive Time Reporting |  | EAS | HRIS | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://hrnet.uihr.uillinois.edu/PTRApplication/index.cfm |  |  | Tony Kerber will need to be involved in deciding. | Tony Kerber will need to be involved in deciding. | Tony Kerber will need to be involved in deciding. | thousands
After August 25, 2014 | Prodagio | Prodagio | EAS | Finance | [5 empty] | N |  |  |  |  | AITS TAM Finance | none identified |  | not needed
Need to identify owner(s) | Production Batch Request Application | edu.uillinois.aits.prodbatchrequest | EAS | [6 empty] | N | [7 empty] | 74
Need to identify owner(s) | PRZM login for EAS | edu.uillinois.aits.PRZM-E | EAS | [6 empty] | N | [7 empty] | thousands
Unknown (Fall 2014) | Quik Pay | edu.uillinois.aits.QuikPAYHelper | EAS | Finance | [5 empty] | N |  |  |  |  | AITS TAM Finance | none identified | In Fall | not needed
Need to identify owner(s) | ReptAccess Request Front End - appserv1 | edu.uillinois.aits.reptaccess | EAS | [6 empty] | N | [7 empty] | 119
After November 2014 | Retro Pay Application | edu.uillinois.aits.retropay | EAS | HR/Pay | [5 empty] | N |  |  |  |  | AITS/HR | After Upgrades/PPACA/Pension Reform | After November 2014
Unknown | Security Application | edu.uillinois.aits.secapp | EAS | [6 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv6.admin.uillinois.edu/appslogin/servlet/appslogin?ReturnURL=http://www.aits.uillinois.edu/cms/One.aspx?portalId=909813&pageId=910631&appName=SP_AITS |  |  | AITS ESA & Security
Unknown (Fall 2014) | Single-Use Account Application | edu.uillinois.aits.SUAccounts | EAS | Finance | [5 empty] | N |  |  |  |  | AITS TAM Finance | none identified | In Fall
Need to identify owner(s) (no user sessions since 6/1/13) | Site Publish - AITS_VAS | SP_AITS_VAS | EAS | [6 empty] | N | [7 empty] | 0
Need to identify owner(s) | Site Publish - AUDITS | SP_AUDITS | EAS | [6 empty] | N | [7 empty] | 46
Need to identify owner(s) | Site Publish - COD | SP_COD | EAS | [6 empty] | N | [7 empty] | thousands
Need to identify owner(s) | Site Publish - ECIO | SP_ECIO | EAS | [6 empty] | N | [7 empty] | 271
Need to identify owner(s) (no user sessions since 6/1/13) | Site Publish - HRFE | SP_HRFE | EAS | [6 empty] | N | [7 empty] | 0
Need to identify owner(s) | Site Publish - STUDENTMONEY | SP_STUDENTMONEY | EAS | [6 empty] | N | [7 empty] | 21
Need to identify owner(s) | Site Publish - TREASURY | SP_TREASURY | EAS | [6 empty] | N | [7 empty] | 203
Need to identify owner(s) | Site Publish - UICHR | SP_UICHR | EAS | [6 empty] | N | [7 empty] | 842
Need to identify owner(s) | Site Publish - UICREADY | SP_UICREADY | EAS | [6 empty] | N | [7 empty] | 11
Need to identify owner(s) | Site Publish - USFSCO | SP_USFSCO | EAS | [6 empty] | N | [7 empty] | 181
Need to identify owner(s) (no user sessions since 6/1/13) | SP_AITS_VAS | (WIDEMEMO) | XAS | [6 empty] | N | [7 empty] | 0
Need to identify owner(s) (no user sessions since 6/1/13) | SP_VENDOR | (WIDEMEMO) | XAS | [6 empty] | N | [7 empty] | 0
2014-07-16 | State Appropriate Control System Application | edu.uillinois.aits.SACSFrontEnd | EAS | Finance | [5 empty] | N | Y | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://webprod.admin.uillinois.edu:443/sacs/index.jsp | N |  | need to identify testers | none identified | In Fall | not needed
Need to identify owner(s) (no user sessions since 6/1/13) | Status-Alert Application | edu.uillinois.aits.status | EAS | [6 empty] | N | [7 empty] | 0
2014-07-22 | Student Mobile | edu.uillinois.aits.studentinfo | EAS | Student | [5 empty] | N |  | https://appserv6.admin.uillinois.edu/StudentInfo/index.jsp?campus=1 |  |  | AITS ADSD TAM Student | none identified | 2014-07-22 | not needed | N | N
2014-07-22 | Student Registration Grouping (Time Ticketing) | edu.uillinois.aits.studreggrp | EAS | Student | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv3.admin.uillinois.edu:443/studreggrp/jsp/index.jsp |  |  | AITS ADSD TAM Student | none identified | 2014-07-22 | not needed | N | N
Unknown (Fall 2014) | Tcard | edu.uillinois.aits.tcard | EAS | Finance | [5 empty] | N |  |  |  |  | AITS TAM Finance | none identified | In Fall | not needed
Unknown (Fall 2014) | TEM | edu.uillinois.aits.TEMHelper | EAS | Finance | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv6.admin.uillinois.edu/appsloginssa/servlet/SelfServiceLogin?appName=edu.uillinois.aits.TEMHelper |  |  | AITS TAM Finance | none identified | In Fall | not needed
Need to identify owner(s) | Test Web Application | edu.uillinois.aits.webapptest | EAS | [6 empty] | N | [7 empty] | 27
2014-07-22 | Transcripts on Demand by SCRIP-SAFE | TranscriptsOnDemand | EAS | Student | [5 empty] | N |  | https://webprod.admin.uillinois.edu/bl/servlet/BannerLogin?appName=TranscriptsOnDemand |  |  | AITS ADSD TAM Student | none identified | 2014-07-22 | not needed | N | N
Anytime | Tuition Waiver Calculator Table Front-end Application | edu.uillinois.aits.fa.twboltonfrontend | EAS | Student | [5 empty] | N |  | https://webprod.admin.uillinois.edu/finaidFrontEnds/twfrontend/index.jsp |  |  | AITS ADSD TAM Student | none identified | Anytime | not needed
2014-07-22 | Tuition Waiver Web Application | edu.uillinois.aits.twfrontend | EAS | Student | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://webprod.admin.uillinois.edu:443/finaidFrontEnds/twfrontend/index.jsp |  |  | AITS ADSD TAM Student | none identified | 2014-07-22 | not needed | N | N
Need to identify owner(s) | u.select - Import Courses | edu.uillinois.aits.CASRIHelper | EAS | [6 empty] | N | [7 empty] | 518
Need to identify owner(s) | uaguest1 |  | BlueStem | [6 empty] | N
| UIC Auxiliary Services Application |  | EAS | [6 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://appserv3.admin.uillinois.edu:443/ssaDeductions/ba_park_emp_search.jsp
Need to identify owner(s) (no user sessions since 6/1/13) | UIC Library Services | edu.uillinois.aits.UicLibraryServicesHelper | EAS | [6 empty] | N | [7 empty] | 0
Need to identify owner(s) (no user sessions since 6/1/13) | UIS Library Services | edu.uillinois.aits.UisLibraryServicesHelper | EAS | [6 empty] | N | [7 empty] | 0
| Unclaimed Bank Wires Web Based Application |  | EAS | [8 empty] | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://apps.obfs.uillinois.edu/uaswires/index.cfm
Need to identify owner(s) | University of Illinois Housing | edu.uillinois.aits.uiHousingBL_illinois | EAS | [6 empty] | N | [7 empty] | thousands
Need to identify owner(s) (no user sessions since 6/1/13) | University of Illinois Housing | edu.uillinois.aits.uiHousingBL | EAS | [6 empty] | N | [7 empty] | 0
Need to identify owner(s) (no user sessions since 6/1/13) | uPortal Demo Project | edu.uillinois.aits.PortalDemo | EAS | [6 empty] | N | [7 empty] | 0
Need to identify owner(s) (no user sessions since 6/1/13) | VasDemoApplication1 | (WIDEMEMO) | XAS | [6 empty] | N | [7 empty] | 0
Need to identify owner(s) | VasFilter | (WIDEMEMO) | XAS | [6 empty] | N | [7 empty] | thousands
Need to identify owner(s) | Vendor Application Service | VDB | EAS | [6 empty] | N | [7 empty] | thousands
Need to identify owner(s) (no user sessions since 6/1/13) | Vendor Registration | edu.uillinois.aits.OCP.VendorRegistration | EAS | [6 empty] | N | [7 empty] | 0
Need to contact Brian Schoudel | ViewDirect |  | EAS | [6 empty] | Y |  | https://docdirectpweb.admin.uillinois.edu/ddrint/servlet/ddrint | N |  |  |  |  | thousands
Need to identify owner(s) | Web Services Support Application | edu.uillinois.aits.webServiceSupport | EAS | [6 empty] | N | [7 empty] | 117
Need to identify owner(s) (no user sessions since 6/1/13) | Webtrans Framework Serving the AITS Web Site | edu.uillinois.aits.Webtrans | EAS | [6 empty] | N | [7 empty] | 0
Need to identify owner(s) (no user sessions since 6/1/13) | Webtrans Framework Serving the AITS Web Site in Development | edu.uillinois.aits.Webtrans.Development | EAS | [6 empty] | N | [7 empty] | 0
Need to identify owner(s) (no user sessions since 6/1/13) | Webtrans Framework Serving the AITS Web Site in Test | edu.uillinois.aits.Webtrans.Test | EAS | [6 empty] | N | [7 empty] | 0
Need to identify owner(s) (no user sessions since 6/1/13) | Webtrans Framework Serving the AITS Web Site in Training | edu.uillinois.aits.Webtrans.Training | EAS | [6 empty] | N | [7 empty] | 0
Anytime | WebXtender (BDMS) Application | edu.uillinois.aits.WebXTender | EAS | Cross-Functional | [5 empty] | N |  |  |  |  | AITS TAM ODA | none identified | Anytime | not needed
Anytime | WebXtender Application - APPSDEV | edu.uillinois.aits.NonBannerWebXTender | EAS | Cross-Functional | [5 empty] | N |  |  |  |  | AITS TAM ODA | none identified | Anytime | not needed
2014-07-22 | Work Study Front End application |  | EAS | Student | [5 empty] | N |  | https://eas.admin.uillinois.edu/eas/servlet/EasLogin?redirect=https://webprod.admin.uillinois.edu:443/finaidFrontEnds/fawsfrontend/index.jsp |  |  | AITS ADSD TAM Student | none identified | 2014-07-22 | not needed | N | N
Need to identify owner(s) (no user sessions since 6/1/13) | XasDemoApplication1 | (WIDEMEMO) | XAS | [6 empty] | N | [7 empty] | 0

## already migrated
APPL_DESCR | APPL_NAME from EAS database) | Migrated to SiteMinder Y/N
BEA Administration Application | edu.uillinois.aits.beaadmin | Y
Database Password Manager | edu.uillinois.aits.passwordManager | Y
Diplomatic Front-end | edu.uillinois.aits.diplomaticfrontend | Y
DSKnowledgeCenter | DSKnowledgeCenter | Y
DSMetaData | DSMetaData | Y
DSPwdMgmt | DSPwdMgmt | Y
DSSecApp | DSSecApp | Y
DSTrainingNet | DSTrainingNet | Y
DSUSCApp | DSUSCApp | Y
Ethics Web Admin Tool | edu.uillinois.aits.EthicsAdminTool | Y
Expected Graduation Date Application | edu.uillinois.aits.expgraddate | Y
FCP Web Application | edu.uillinois.aits.FCPWebHelper | Y
FormBuilderAdmin | FormBuilderAdmin | Y
FormBuilderSurvey | FormBuilderSurvey | Y
GradeChangeSystem | GradeChangeSystem | Y
I9TrackerSSO | I9TrackerSSO | Y
IllinoisProfiles | IllinoisProfiles | Y
Map Calculator Table Front-end Application | edu.uillinois.aits.mapfrontend | Y
Moodle | Moodle | Y
NESSIE Application | edu.uillinois.uihr.Nessie | Y
NEWT | edu.uillinois.uihr.HrNet | Y
NextGen Dynamic Forms | NextGenForms | Y
PEAR (Protected Email Attachment Repository) Application | edu.uillinois.aits.PearApplication | Y
PEAR (Protected Email Attachment Repository) Application - Test Environment | edu.uillinois.aits.PearApplication.Test | Y
PRMS (Personnel Register Management System) | edu.uillinois.aits.prms | Y
Secure Access Application | edu.uillinois.aits.secureAccess | Y
Site Publish - AITS | SP_AITS | Y
Site Publish - APPSCERTIFY | SP_APPSCERTIFY | Y
Site Publish - Board of Trustees | SP_TRUSTEES | Y
Site Publish - CCFD | SP_CCFD | Y
Site Publish - DATACENTER | SP_DATACENTER | Y
Site Publish - ETHICS | SP_ETHICS | Y
Site Publish - FLYCMI | SP_FLYCMI | Y
Site Publish - FOIA | SP_FOIA | Y
Site Publish - HR | SP_HR | Y
Site Publish - ICAC | SP_ICAC | Y
Site Publish - ITPC | SP_ITPC | Y
Site Publish - OBFS | SP_OBFS | Y
Site Publish - PB | SP_PB | Y
Site Publish - SCSCAREERS | SP_SCSCAREERS | Y
Site Publish - SSN | SP_SSN | Y
Site Publish - State Univ. | SP_STATEUNIV | Y
Site Publish - Strategic Plan | SP_STRATEGICPLAN | Y
Site Publish - UICEHSO | SP_UICEHSO | Y
Site Publish - UICOIS | SP_UICOIS | Y
Site Publish - UILLINOIS | SP_UILLINOIS | Y
Site Publish - UIS | SP_UIS | Y
Site Publish - UISLIBRARY | SP_UISLIBRARY | Y
Site Publish - UOCPRES | SP_UOCPRES | Y
Site Publish - UTMT | SP_UTMT | Y
Site Publish - VENDOR | SP_VENDOR | Y
Site Publish - VPAA | SP_VPAA | Y
Site Publish - Web | SP_WEB | Y
SSA Front-end Application | edu.uillinois.aits.ssafrontend | Y
Transfer Credit Extract Front-end | edu.uillinois.aits.tcefrontend | Y
UICHRPERS appslogin helper | UICHRPERS | Y
Upside | edu.uillinois.aits.UpsideHelper | Y
UTMT Web Site | UTMT_Site | Y
Withdrawal Front-end | edu.uillinois.aits.rr.withdraw | Y
National Student Clearinghouse | https://webprod.admin.uillinois.edu/ssa/servlet/SelfServiceLogin?appName=edu.uillinois.aits.NSCHelper&campus=1 | y
HR Adjustment Authorization Management Application (duplicate of Maintenance of Workflow Departmental Approvers) | edu.uillinois.aits.hrPayAdjAuth | Y
UniCenter |  | Y
NOA |  | Y
PHDCOS (Payroll History Database and Change of Status) | edu.uillinois.aits.phdcos | Y
Maintenance of Workflow Departmental Approvers | duplicate of HR Adjustment Authorization Management Application | Y

## not being used
APPL_DESCR | APPL_NAME from EAS database) | EAS or XAS app | Notes from TAM/ESC
edu.uillinois.aits.Desire2LearnHelper - Not being used | edu.uillinois.aits.Desire2LearnHelper | EAS
edu.uillinois.aits.ElluminateHelper - Not being used | edu.uillinois.aits.ElluminateHelper | EAS
edu.uillinois.aits.gcctrltable.GCFrontEnd - Not being used | edu.uillinois.aits.gcctrltable.GCFrontEnd | EAS
edu.uillinois.aits.GCPOSSetup - Not used | edu.uillinois.aits.GCPOSSetup | EAS
edu.uillinois.aits.GCRegistration - Not being used | edu.uillinois.aits.GCRegistration | EAS
edu.uillinois.aits.GCServiceHelper - Not being used | edu.uillinois.aits.GCServiceHelper | EAS
eSupport for Clarify - Not Used | edu.uillinois.aits.ESupportLogin | EAS
GFAS Fund Code - Not used | edu.uillinois.aits.gcGFASFundCode | EAS
Global Campus reset claiming PIN - Not used | edu.uillinois.aits.GCUnexpire | EAS
Global Campus reset claiming PIN - Not used | CPRES_Site | EAS
GPGS Web Application - Not being used | edu.uillinois.aits.gpgsfrontend | EAS
Paymaster Batch Error Web Application - Not Being Used | edu.uillinois.aits.PaymasterBatchErrorViewer | EAS |  | N
HRFE | HRFE_Site | EAS
Applications Certifications | CERT_Site | EAS
Campus Center | edu.uillinois.aits.CampusCenterHelper | EAS
Change Control Application - Read Only | edu.uillinois.aits.changecontrol | EAS
CVS Monitoring Web Application | edu.uillinois.aits.cvsmonitor | EAS
CVS Web Application | edu.uillinois.aits.CVSWebBL | EAS
CVS Web Application | edu.uillinois.aits.CvsWeb | EAS
Destination Poller Application | edu.uillinois.aits.DestinationPollerApplication | EAS
Drupal_Site | Drupal_Site | EAS
EAS Demo Application | edu.uillinois.aits.EasDemoApplication1 | EAS
Financial Engineering Club Web Site | FEC_Site | EAS
Pending Degree List Application ***No longer a Production Application*** | edu.uillinois.aits.penddeglist
College Admissions Interface | edu.uillinois.aits.caifrontend | EAS | ???? - this app is not a production app